## Tasks
Task ID | Task Name | Lists | Assignee | Due Date | Status
256nvjr | Charge Controller IC/circuit | Circuit Design | Seth | 2022-01-22 | OPEN
256nvjt | Battery back with fuse and temp sensors | Circuit Design | Dan T | 2022-01-22 | OPEN
256nvju | +5V Regulator IC/Circuit | Circuit Design | Alec | 2022-01-22 | OPEN
256nvjv | Microcontroller Interfacing | Circuit Design | Dan P | 2022-01-22 | OPEN
256nvq0 | Integrate parts into master paper schematic | Circuit Design |  | 2022-02-05 | OPEN
256nvm1 | Choose design software | PCB Schematic |  | 2022-01-22 | CLOSED
256nvq7 | Transfer master schematic into software | PCB Schematic |  | 2022-02-05 | OPEN
256nvr8 | Perform layout | PCB Layout |  | 2022-02-26 | OPEN
256nvxv | Review Design | PCB Layout |  | 2022-02-28 | OPEN
256nyrh | Wait for delivery | PCB Layout |  | 2022-03-12 | OPEN
256nvyr | Create test plan | PCB Bench Test |  | 2022-03-12 | OPEN
256nvz9 | Perform bench testing/ Problem Solving | PCB Bench Test |  | 2022-03-26 | OPEN
256p0rk | Integrate into flight vehicle | PCB Integration |  | 2022-04-02 | OPEN